## Sheet1
STANDARD OPERATING PROCEDURE FOR UNITS OF MEASUREMENT ON ADVERTISED CONSTRUCTION CONTRACTS
Unit Represents Payment Via a Measured Quantity or Lump Sum Effective Date: 01 October 2004
# | ITEM | UNIT | REMARKS
1 | Hydraulic Dredging - ED | CY | applies to all jobs originating in Engineering Division
2 | Hopper Dredging - ED | CY | applies to all jobs originating in Engineering Division
3 | Hydraulic Dredging - OD | HRS | applies to all jobs originating in Operations Division
4 | Hopper Dredging - OD | HRS | applies to all jobs originating in Operations Division
5 | Pile Dike
| - Piles | LF
| - Wales | LF
6 | Guide Walls
| - Piles | LF
| - Guidewalls and Fenders | LS
| - Wales, Thrust Blocks, Shear Blocks and Girts | LF
7 | Dolphins - Sheet Piling
| - Sheet Piling | SF | sheet pile is broken out separated from the rest of the dolphin
| - New Dolphin | LS | remaining features of work
8 | Rock / Stone | TONS | measured by barge displacement or truck measure
9 | Bedding | CY | truck measure
|  | TONS | barge displacement measurement
10 | Surfacing | CY | truck measure
11 | Geotextile | SY | in-place measurement
12 | Pipe | LF | in-place measurement
13 | Catch Basins and Manholes | EA | use separate items for different types
14 | Dewatering | LS | contractor design
15 | Structural Excavation | LS | specifications or drawings must delineate the quantity
16 | Structural Backfill | LS | specifications or drawings must delineate the quantity
17 | Channel Excavation | CY | measured by the end-area method
18 | Canal Excavation | CY | truck measure
19 | Clearing and Grubbing - Levee Work
| - Levee Work | LS | undefined quantity based on borrow and to fill estimated for job
| - Misc. | n/a | less than $50,000 placed in job overhead
20 | Levee Embankments | CY | measured by the end-area method with settlement plates
21 | Earthen Dikes | LS | contractor designed
22 | Sheet Piles | SF | measured by projected area - length x depth
may be broken out into separate items for furnishing and driving
23 | H-Piles | LF | may be broken out into separate items for furnishing and driving
24 | Timber Piles | LF | may be broken out into separate items for furnishing and driving
25 | Concrete Piles | LF | may be broken out into separate items for furnishing and driving
26 | Temporary Sheet Piling | SF | when Corps designed
|  | LS | when contractor designed
27 | Work Platform | LS | contractor designed where required
28 | Pile Load Tests | EA | may include subdivided items
Examples: AA. "First 4 Tests" and AB. "All Over 4 Tests"
29 | Pile Caps | EA | when all caps are of uniform section; includes costs for all forming, rebar, finishing, etc.
|  | LS | when dimensions vary; includes costs for all forming, rebar, finishing, etc.
30 | Bridge Deck
| - Precast Girders | LF | includes costs for all forming, rebar, finishing, etc.
| - Deck Paving | SY | includes costs for all forming, rebar, finishing, etc.
31 | Concrete Paving | SY | separate items for each thickness; includes costs for all forming, rebar, finishing, etc.
32 | Road Sub-Base | SY | separate items for each thickness
|  | CY | measured by truck measure
33 | Concrete Curb | LF | use separate items for barrier curb, rollover curb, etc.; includes costs for all forming, rebar, etc.
includes costs for all forming, rebar, finishing, etc.
34 | Guardrail | LF
35 | Concrete Slope Paving | SQ | 1 SQ = 100 SF
quantity includes cutoff walls; includes costs for all rebar, forming, etc.
36 | Concrete I-Walls | LF | uniform cross-section; includes costs for all forming, rebar, finishing, etc.
|  | LS | non-uniform cross-section; includes costs for all forming, rebar, finishing, etc.
37 | Concrete T-Walls | LS | includes costs for all forming, rebar, finishing, etc.
38 | Concrete Flumes and Box Culverts | LF | uniform cross-section; includes costs for all forming, rebar, finishing, etc.
|  | LS | non-uniform cross-section; includes costs for all forming, rebar, finishing, etc.
39 | Asphalt | SY
|  | TONS | measured by truck at plant
40 | Flood Gates | LS | exception - under supply contracts paid for by the pound.
41 | Miter Gates | LS | exception - under supply contracts paid for by the pound.
42 | Sector Gates | LS | exception - under supply contracts paid for by the pound.
43 | Suice Gates | EA
44 | Valves | EA
45 | Fencing | LF
| - Permanent Fencing | LF
| - Silt Fencing | LF or n/a | paid for by the linear foot when over $10,000; otherwise covered in job overhead
| - Safety Fencing | LF or n/a | paid for by the linear foot when over $10,000; otherwise covered in job overhead
| - Silt and Safety Fencing | LF | when both items are along uniform placement they may be covered under a common bid item
46 | Fertilizing, Seeding and Mulching | Acre | vendor letter prompted NOD policy of quantifying bid items
47 | Sodding | Acre
48 | Electrical | LS | features of work may be separated into separate line items
49 | Mechanical
- Pumping Station
| - Pump Engines | EA
| - Gear Reducers | EA
| - Pumps | EA
50 | Miscellaneous Metalwork | LS
51 | Painting / Coatings - Sheetpile
| - Sheetpile | SF or n/a | may be paid for separately or within the sheet pile item
| - Pipes | n/a | usually included in the pipe item
| - Floodwalls | SF or n/a | may be paid for separately or within the floodwall item